## Project Tracker
Objective | Initiative | Start Date | End Date | Department | Manager | Status | Progress (%) | Visual | Comments | Dependencies
Enhance Customer Experience: Reduce customer support response time by 20% | Implement Customer Feedback Portal: Launch by Q2 2026 | 2025-01-04 | 2026-01-04 | Customer Support | Miss X | Planning | 10 |  | Kickoff meeting set for next week, awating vendor contact approval Meeting Minutes: Vendor selection finalized. Task List: 1. Design UI/UX, 2. Develop backend, 3. Integrate with CRM. Progress Update: UI/UX design 50% complete | IT infrastructure setup
Streamline Internal Processes | Reduce manual effort in sales order creation | 1/16/2025 | 7/31/2025 | Sales | Mr. Y | In Progress | 50 |  | IT installing automation component | SAP Note installation
Develop New Product Line | Expand into automative industry | 2024-01-01 | 2025-01-05 | Sales | Mr. Y | Completed | 100 |  | New product launched ahead of schedule | N/A
Enhance Employee Training | Develop eLearning and Instructor-led trainings | 2025-05-02 | 2025-10-10 | Operations | Mrs. T | Blocked | 15 |  | Contracting issues need to be resolved before continuing | Contact negotiation

## Project Overview
Total Number of Projects | 4
Not Started | 0
Planning | 1
In Progress | 1
Completed | 1
Blocked | 1